College Event Planning & Review

Proposed next edition plan · KIT / TNWISE · Verify event-specific facts before submission

# 1. Event choice and purpose

Proposed plan: TNWISE next edition / student innovation showcase associated with KIT. This is a planning proposal, not a claim that a future event is approved or scheduled.

Personal context to confirm before recording: I have participated in TNWISE 2025 and 2026, and our team presented a project in 2026. Replace or correct this sentence if needed.

Purpose: give student teams a structured platform to present applied technology projects, receive feedback, and communicate their problem, solution, prototype, and impact. Audience: KIT students and faculty; invited reviewers/industry guests only if approved.

Evidence and scale: use only a real poster, college announcement, calendar, or your own permitted participation evidence. I have not verified a published headcount or venue capacity, so the plan uses a pilot estimate of 8–12 teams and 40–70 attendees for budgeting only. Confirm capacity and registration with the college.

# 2. Goals and success measures

Primary goal: run a safe, on-time student project showcase that gives every registered team a fair presentation and feedback opportunity.

Targets (proposed, not historical results): 8–12 teams; at least 80% of registered teams present; at least 80% attendee satisfaction from a short feedback form; finish within 15 minutes of the published schedule; reconcile 100% of approved spending with receipts.

Record registrations, actual check-ins, teams presented, feedback responses, spend versus approved budget, schedule variance, and issues resolved. Report actual results after the event rather than presenting targets as results.

# 3. Timing and pre-production

Timing: propose a half-day slot on a non-exam weekday, after checking the KIT academic calendar, internal assessments, lab availability, and faculty availability. Do not publish a date until the department/faculty coordinator confirms it.

Preparation timeline: T–4 weeks: confirm event owner, objective, date window, audience and venue; draft brief and budget. T–3 weeks: seek approvals; invite teams and reviewers. T–2 weeks: open registration; publish approved poster and rules. T–1 week: confirm teams, presentation order, equipment and accessibility needs. T–2 days: test projector, microphones, laptop, Wi-Fi and backup files. T–1 day: send final schedule and role sheet. Event day: check-in, briefing, presentations, feedback, closing. T+1–3 days: share approved highlights, collect feedback, reconcile budget and write review.

# 4. Proposed schedule and roles

09:00–09:30 — setup, AV check, registration desk and signage. 09:30–09:40 — welcome and safety/housekeeping. 09:40–10:00 — event purpose and judging/feedback criteria. 10:00–11:30 — team demos, with 7 minutes per team plus 2 minutes for questions (adjust to approved team count). 11:30–11:45 — break and evaluator scoring. 11:45–12:15 — remaining demos / showcase walk-through. 12:15–12:30 — feedback highlights and recognition. 12:30–12:40 — closing and group photo only with permission. 12:40–13:00 — pack-down and equipment check.

Roles: faculty coordinator (approval and escalation); student lead (run-of-show and decisions); registration team (check-in and headcount); stage/timekeeper (keeps demos on time); AV support (projector/audio/backup); reviewer liaison (briefs reviewers and collects feedback); media lead (only approved photos/video); finance/procurement contact (approved spend and receipts). Assign named people only after consent and confirmation.

# 5. Budget / resources (planning estimate)

Planning estimate for a small campus showcase; not an approved quote: printing/signage ₹800; water/refreshments ₹2,500; certificates ₹700; basic stationery ₹300; contingency ₹700. Estimated total ₹5,000. Venue, projector, microphones, chairs and electricity are assumed to be provided by the college at no extra cost; confirm this before approval.

Do not commit or purchase before budget approval. If refreshments or printing are not approved, use digital signage and water available through the department. Keep receipts and record actual spend.

# 6. Promotion and registration

Use only channels approved by the department: college/department notice board, official student groups, class representatives, and a faculty-approved digital poster. Poster content: event name, purpose, eligibility, date/time (only after confirmation), venue, registration deadline, team-size limit (to be decided), submission/demo requirements, contact through the official coordinator, and accessibility/safety notes.

Use a simple registration form collecting only necessary details: team name, project title, team size, presenter, equipment needs and consent for optional recording. Share an agenda and presentation rules with registered teams. Track registrations separately from actual attendance.

# 7. Approvals and risk handling

Before announcing: obtain faculty/department approval for the event brief, date, venue, budget, poster/branding, external reviewers, equipment, and photography/video. Ask campus IT/AV staff about network and electrical setup. Confirm emergency access and venue rules.

Risks and responses: projector/network failure — keep offline slides and a spare laptop; a team runs late — timekeeper uses a visible timer and a buffer; low registration — ask class representatives to circulate the approved call and reduce setup costs; overspend — pre-approve a cap and require receipts; participant privacy concern — provide a no-photo option and avoid publishing identifiable footage without consent; schedule conflict — keep a backup date pending faculty approval.

# 8. Recording and post-production

Shot list: event signage/room setup; presenter at a distance; close-up of prototype only where safe; audience wide shots only if permitted; reviewer feedback without recording private discussion; awards/closing only with consent; short clips of project demos after checking IP/confidentiality.

Before recording, get college permission and informed consent from identifiable participants. Offer a clear no-recording option; do not publish registration lists or personal contact details. After the event, select relevant clips, remove accidental personal information, add captions, check project/IP permissions, and submit the final cut for faculty approval before posting.

# 9. Post-event review and contribution

Within 1–3 days, compare targets with actual check-ins, team presentations, satisfaction, schedule adherence, incidents and spend. Hold a 15-minute team debrief: what worked, what failed, what should change. Store the approved agenda, final budget, anonymised feedback summary, attendance count and approved media in the college-approved folder.

Contribution statement for the video: explain only the tasks you personally owned. Separate them from tasks completed by the faculty coordinator or other students. If you are proposing the next edition rather than reporting a completed one, say clearly that the schedule, budget, targets and approvals are proposed assumptions.

# 10. Items to verify before submission

Confirm with your own knowledge whether TNWISE is the correct named event for your assignment and how it is formally associated with KIT.

Add one real, permitted piece of evidence (event poster/announcement/calendar or your own project participation proof). Do not fabricate an attendance number or approval.

Replace the planning estimates if you find official figures. Keep the proposed event date and approvals labelled as pending until confirmed.